## Outputs
State | Region | State Id | Funding stream | AG Id | Output Id | Output Title | Output code (1–103 + 401–409) | Output Code | Output Type | Standard Output | Output Unit of Measure #1 | Total Actual #1 | Actual 02-03 #1 | Actual Jul 03- Mar 04 #1 | Actual Apr-Jun 04 #1 | Expected 04–05 #1 | Actual 04-05 #1 | Expected Jul-Dec 2005 #1 | Actual Jul-Dec 2005 #1 | Expected 2005-06 #1 | Actual 2005-06 #1 | Output Unit of Measure #2 | Total Actual #2 | Actual 02-03 #2 | Actual Jul 03- Mar 04 #2 | Actual Apr-Jun 04 #2 | Expected 04–05 #2 | Actual 04-05 #2 | Expected Jul-Dec 2005 #2 | Actual Jul-Dec 2005 #2 | Expected 2005-06 #2 | Actual 2005-06 #2 | Reasons for overall variance (max 180 characters) | Category of Primary Reason for Overall Variance | Is output complete (i.e. no more action required)? Y/N | Comment
Queensland | State-wide | WLNRM01 | NHT |  | 1 | Understanding Queensland's Wetlands -- Series of meetings with wetland researchers in northern region | 14 | CB2.1 | Capacity building | Skills and training | Number of training sessions, workshops, seminars or other skills and training events conducted | 1 | 0 | 0 | 0 | 1 | 1 |  |  | 0 | 0 | Number of participants in person-days | 6 | 0 | 0 | 0 | 6 | 6 |  |  | 0 | 0 | 0 | 0 | y | 0
Queensland | State-wide | WLNRM01 | NHT |  | 7 | External review of draft report |  | CB4.3 | Capacity building | Organisational learning | Number of organisational learning reviews completed | 0 | [7 empty] | 0 | 0 | - | [10 empty] | 0 | 0 | n
Queensland | State-wide | WLNRM01 | NHT |  | 2 | Understanding Queensland's Wetlands -- workshops | 14 | CB2.1 | Capacity building | Skills and training | Number of training sessions, workshops, seminars or other skills and training events conducted | 4 | 0 | 0 | 0 | 1 | 1 | 2 | 3 | 2 | 3 | Number of participants in person-days |  | 0 | 0 | 0 | 6 | 6 |  |  |  |  | 0 | 0 | y | 0
Queensland | State-wide | WLNRM01 | NHT |  | 3 | Understanding Queensland's Wetlands -- draft workshop reports | 14 | RA2.3 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of reports completed | 5 | 0 | 0 | 0 | 1 | 1 | 3 | 4 | 3 | 4 | - |  | 0 | 0 | 0 | 6 | 6 |  |  |  |  | 0 | 0 | y | draft
Queensland | State-wide | WLNRM01 | NHT |  | 4 | Understanding Queensland's Wetlands -- seminar at Wetlands Forum, Newcastle NSW | 14 | CB2.1 | Capacity building | Skills and training | Number of training sessions, workshops, seminars or other skills and training events conducted | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | Number of participants in person-days |  | 0 | 0 | 0 | 6 | 6 |  |  |  |  | 0 | 0 | y | 0
Queensland | State-wide | WLNRM01 | NHT |  | 5 | Factsheet for project completed and on EPA website | 14 | CB1.2 | Capacity building | Awareness raising | Number of written products such as brochures, newsletters, posters or fact sheets developed | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Estimated number of recipients |  | 0 | 0 | 0 | 6 | 6 |  |  |  |  | 0 | 0 | y | 0
Queensland | State-wide | WLNRM01 | NHT |  | 6 | Database of wetland references |  | RA3.2 | Decision support tools | Number of information management systems developed |  | 1 |  |  |  | - | [5 empty] | 0 | 0 | [11 empty] | y
Queensland | State-wide | WLNRM01 | NHT |  | 5 | Draft Report: Understanding ecological and biophysical processes in Queensland's wetlands: a literature review and gap analysis |  | RA4.1 | Resource assessment | Research and development studies | Number of research and development studies completed | 1 | [5 empty] | 1 | 1 (draft) | [13 empty] | Reviewing processes has taken more time than expected. | Other | y | draft

## LookupLists
State | State - Region | Region | Funding Program | Funding Stream | Primary Activity Type | MAT Category | MAT Rating | RCT Rating | PrimaryMfT | Output Selection No | Output Type | Standard Output | Output Unit of Measure #1 | Output Unit of Measure #2 | MAT Year | RCT Year | New_Output_Code | New_Output_Type | New_Standard_Output | New_OUM1 | New_OUM2 | Category_of_Primary_Reason_for_Overall_Variance
Australian Capital Territory | ACT | Australian Capital Territory | NAP | Foundation funding | Capacity building | Adoption of improved practices | (5) Target achieved or exceeded | (5) Evidence of target achieved or exceeded | Land salinity | 0 | Still to be coded | Still to be coded | Still to be coded | Still to be coded | ***tba*** | ***tba*** | CB1.1 | Capacity building | Awareness raising | Number of awareness raising events such as demonstrations, field days or study tours conducted | Number of participants in person-days | Financial
New South Wales | NAT | Cross-jurisdictional | NHT | Priority action | On-ground activities | Capacity building | (4) Progress, and on track | (4) Evidence of progress | Soil condition | 1 | Capacity building | Awareness raising activities | Number of demonstrations | Number of participants in person-days | 2003-04 | 2003-04 | CB1.2 | Capacity building | Awareness raising | Number of written products such as brochures, newsletters, posters or fact sheets developed | Estimated number of recipients | Technical
Northern Territory | NAT | External Territories | NLP | Regional investment | Planning | On-ground activities | (3) Progress, but not on track | (3) Evidence of no progress | Rivers and wetlands | 2 | Capacity building | Awareness raising activities | Number of field days | Number of participants in person-days | 2004-05 | 2004-05 | CB1.3 | Capacity building | Awareness raising | Number of displays for use at events such as regional meetings developed | - | Environmental
Queensland | NAT | Multi-lateral | NAP/NHT | Regional competitive | Resource assessment | Planning | (2) No progress, but some progress was expected | (2) Evidence of regress | Nutrients in aquatic environments | 3 | Capacity building | Awareness raising activities | Number of study tours | Number of participants in person-days | 2005-06 | 2005-06 | CB1.4 | Capacity building | Awareness raising | Number of media opportunities resulting in articles in newspapers or on radio or television created | - | Managerial
South Australia | NAT | Multi-regional | NAP/NLP | Multi-lateral activities | *** tba *** | Resource assessment | (1) No progress, but none expected at this time | (1) Insufficient evidence to assess | Turbidity in aquatic environments | 4 | Capacity building | Awareness raising activities | Number of other non-training forums | Number of participants in person-days | 2006-07 | 2006-07 | CB1.5 | Capacity building | Awareness raising | Number of websites developed or significantly enhanced | - | Other
Tasmania | NAT | State-wide | NHT/NLP | NIS State-wide |  |  | ***tba*** | ***tba*** | Surface water salinity | 5 | Capacity building | Awareness raising activities | Number of brochures developed | Quantity distributed | 2007-08 | 2007-08 | CB2.1 | Capacity building | Skills and training | Number of training sessions, workshops, seminars or other skills and training events conducted | Number of participants in person-days | Still to be coded
Victoria | NSW | Border Rivers - Gwydir | NAP/NHT/NLP | NAP Multi-regional |  |  |  |  | Native vegetation | 6 | Capacity building | Awareness raising activities | Number of newsletters developed | Quantity distributed | 2008-09 | 2008-09 | CB2.2 | Capacity building | Skills and training | Number of workbooks, course notes or other key materials developed | Quantity distributed
Western Australia | NSW | Central West | NUF | NIS Facilitator and co-ordinator |  |  |  |  | Significant native species | 7 | Capacity building | Awareness raising activities | Number of displays developed | Quantity distributed | 2009-10 | 2009-10 | CB3.1 | Capacity building | Establishing new institutional arrangements | Number of key organisational documents produced | -
Multi-lateral | NSW | Hawkesbury - Nepean | ***tba*** | National Landcare Program |  |  |  |  | Significant invasive species | 8 | Capacity building | Awareness raising activities | Number of other non-training products or materials developed | Quantity distributed | 2010-11 | 2010-11 | CB3.2 | Capacity building | Establishing new institutional arrangements | Number of formally documented collaborative arrangements developed | -
Other | NSW | Hunter - Central Rivers |  | ***tba*** |  |  |  |  | Estuarine, coastal and marine | 9 | Capacity building | Awareness raising activities | Number of media opportunities | Not applicable | 2011-12 | 2011-12 | CB3.3 | Capacity building | Establishing new institutional arrangements | Number of arrangements for effective collaboration negotiated where a formal agreement does not exist | -
| NSW | Lachlan | [6 empty] | Other supporting activities | 10 | Capacity building | Awareness raising activities | Number of websites developed | Not applicable | 2012-13 | 2012-13 | CB4.1 | Capacity building | Organisational learning | Number of governance tools developed | -
| NSW | Lower Murray Darling | [6 empty] | ***tba*** | 11 | Capacity building | Facilitation motivation and support activities | Number of FTE active community support positions (facilitators or coordinators) | Not applicable | 2013-14 | 2013-14 | CB4.2 | Capacity building | Organisational learning | Number of significant knowledge evaluation events held | -
| NSW | Murray | [7 empty] | 12 | Capacity building | Facilitation motivation and support activities | Number of community groups or community projects assisted | Not applicable | 2014-15 | 2014-15 | CB4.3 | Capacity building | Organisational learning | Number of organisational learning reviews completed | -
| NSW | Murrumbidgee | [7 empty] | 13 | Capacity building | Skills and training activities | Number of training sessions held | Number of participants in person-days | 2015-16 + | 2015-16 | CB4.4 | Capacity building | Organisational learning | Number new databases developed | -
| NSW | Namoi | [7 empty] | 14 | Capacity building | Skills and training activities | Number of workshops held | Number of participants in person-days |  | 2016-17 | CB5.1 | Capacity building | Community Support | Number of community groups OR projects assisted | -
| NSW | Northern Rivers | [7 empty] | 15 | Capacity building | Skills and training activities | Number of seminars held | Number of participants in person-days |  | 2017-18 | OG1.1 | On-ground | Conservation by agreements | Number of conservation covenants or other agreements attached to title negotiated | Area (ha) protected
| NSW | Southern Rivers | [7 empty] | 16 | Capacity building | Skills and training activities | Number of other skills and training events held | Number of participants in person-days |  | 2018-19 | OG1.2 | On-ground | Conservation by agreements | Number of voluntary conservation agreements negotiated | Area (ha) protected
| NSW | State-wide | [7 empty] | 17 | Capacity building | Skills and training activities | Number of workbooks developed | Quantity distributed |  | 2019-20 | OG10.1 | On-ground | Works related to the improved management of surface or groundwater | Area (ha) of land treated through surface drainage | Length (km) of drain
| NSW | Sydney Metro | [7 empty] | 18 | Capacity building | Skills and training activities | Number of course notes developed | Quantity distributed |  | 2020-21 | OG10.2 | On-ground | Works related to the improved management of surface or groundwater | Area (ha) of land treated through sub-surface drainage | Length (km) of drain
| NSW | Western | [7 empty] | 19 | Capacity building | Skills and training activities | Number of other key materials developed | Quantity distributed |  | 2021-22 | OG10.3 | On-ground | Works related to the improved management of surface or groundwater | Area (ha) of land treated through improvements to existing drainage systems | Length (km) of drain improved
| NT | Daly | [7 empty] | 20 | On-ground activities | Conservation by agreements | Number of legal conservation covenants and other legal agreements | Area (hectares) covered |  | 2022-23 | OG10.4 | On-ground | Works related to the improved management of surface or groundwater | Area (ha) of land treated for rising groundwater through groundwater pumping | -
| NT | Darwin Katherine | [7 empty] | 21 | On-ground activities | Conservation by agreements | Number of voluntary conservation agreements | Area (hectares) covered |  | 2023-24 | OG11.1 | On-ground | Works for improving waterway health | Length (m) of stream bank stabilised with engineering works | -
| NT | Mary river | [7 empty] | 22 | On-ground activities | Indigenous vegetation protected by fencing | Area (hectares) of terrestrial indigenous vegetation protected by fencing | Not applicable |  | 2024-25 | OG11.2 | On-ground | Works for improving waterway health | Length (m) of stream bed stabilised | -
| NT | Northern Territory | [7 empty] | 23 | On-ground activities | Indigenous vegetation protected by fencing | Area (hectares) of coastal indigenous vegetation protected by fencing | Not applicable |  | 2025-26 | OG11.3 | On-ground | Works for improving waterway health | Number of off-stream (alternative) watering sites installed | Length (km) of stream bank protected from stock
| NT | Ord | [7 empty] | 24 | On-ground activities | Indigenous vegetation protected by fencing | Area (hectares) of riparian indigenous vegetation protected by fencing | Streambank length (km) of riparian vegetation protected |  | 2026-27 | OG11.4 | On-ground | Works for improving waterway health | Length (kilometres) of in-stream habitat established | -
| QLD | Border Rivers-Balonne-Maranoa | [7 empty] | 25 | On-ground activities | Indigenous vegetation enhanced/rehabilitated | Area (hectares) of terrestrial indigenous vegetation enhanced/rehabilitated | Not applicable |  | 2027-28 | OG11.5 | On-ground | Works for improving waterway health | Number of fish barriers modified and/ or removed | -
| QLD | Burdekin | [7 empty] | 26 | On-ground activities | Indigenous vegetation enhanced/rehabilitated | Area (hectares) of coastal indigenous vegetation enhanced/rehabilitated | Not applicable |  | 2028-29 | OG12.1 | On-ground | Works for improving water quality | Number of new sewage plants constructed | Volume (ML) of effluent removed or contained by sewage plant
| QLD | Burnett - Mary | [7 empty] | 27 | On-ground activities | Indigenous vegetation enhanced/rehabilitated | Area (hectares) of riparian indigenous vegetation enhanced/rehabilitated | Streambank length (km) of riparian vegetation enhanced/rehabilitated |  | 2029-30 | OG12.2 | On-ground | Works for improving water quality | Number of sewage plants improved with better treatment processes | Volume (ML) of effluent removed or contained by sewage plant
| QLD | Cape York | [7 empty] | 28 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to terrestrial indigenous species | Not applicable |  | 2030-31 + | OG12.3 | On-ground | Works for improving water quality | Number of human effluent disposal sites other than sewage plant constructed | Volume (ML) of effluent removed or contained by effluent control works
| QLD | Condamine | [7 empty] | 29 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to coastal indigenous species | Not applicable |  |  | OG12.4 | On-ground | Works for improving water quality | Number of effluent control works for animal waste established on properties | Volume (ML) of effluent removed or contained by effluent control works
| QLD | Desert Channels | [7 empty] | 30 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to riparian indigenous species | Streambank length (km) of riparian vegetation protected |  |  | OG12.5 | On-ground | Works for improving water quality | Number of other effluent or farm runoff control works established on properties | Volume (ML) of effluent removed or contained by effluent control works
| QLD | Fitzroy | [7 empty] | 31 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of terrestrial exotic perennial pastures | Not applicable |  |  | OG12.6 | On-ground | Works for improving water quality | Number of stormwater quality control devices constructed | Kg of material prevented from entering waterway per years
| QLD | Mackay - Whitsunday | [7 empty] | 32 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of coastal exotic perennial pastures | Not applicable |  |  | OG12.7 | On-ground | Works for improving water quality | Number of constructed wetlands | Area of constructed wetlands
| QLD | Northern Gulf | [7 empty] | 33 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of riparian exotic perennial pastures | Not applicable |  |  | OG13.1 | On-ground | Works related to improving water use efficiency | Area (ha) of land where improved irrigation practices have been adopted | Number of land managers using improved irrigation practices
| QLD | South East Queensland and Western Catchments Group | [7 empty] | 34 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of terrestrial exotic plantation | Not applicable |  |  | OG13.2 | On-ground | Works related to improving water use efficiency | Number of on-farms reuse systems constructed | Volume (ML) of water saved per year
| QLD | South West | [7 empty] | 35 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of coastal exotic plantation | Not applicable |  |  | OG13.3 | On-ground | Works related to improving water use efficiency | Number of land managers who have adopted on-farm water saving practice by drainage diversion | Volume (ML) of water saved per year
| QLD | Southern Gulf | [7 empty] | 36 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of riparian exotic plantation | Not applicable |  |  | OG13.4 | On-ground | Works related to improving water use efficiency | Length (km) of channel improved or piped if applicable | Volume (ML) of water saved per year
| QLD | Torres Strait | [7 empty] | 37 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of other terrestrial exotic or mixed indigenous/exotic vegetation planted | Not applicable |  |  | OG13.5 | On-ground | Works related to improving water use efficiency | Number of groundwater bores capped | Volume (ML) of water saved per year
| QLD | Wet Tropics | [7 empty] | 38 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of other coastal exotic or mixed indigenous/exotic vegetation planted | Not applicable |  |  | OG13.6 | On-ground | Works related to improving water use efficiency | Number of new stormwater reuse systems | Volume (ML) of water saved per year
| SA | Alinytjara Wilurara | [7 empty] | 39 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of other riparian exotic or mixed indigenous/exotic vegetation planted | Not applicable |  |  | OG2.1 | On-ground | Native vegetation protected by fencing | Area (ha) of coastal native vegetation protected by fencing | -
| SA | Eyre Peninsula | [7 empty] | 40 | On-ground activities | Riparian and waterway health | Length (km) of stream bank stabilised | Number of structures |  |  | OG2.2 | On-ground | Native vegetation protected by fencing | Area (ha) of wetland native vegetation protected by fencing | -
| SA | Kangaroo Island | [7 empty] | 41 | On-ground activities | Riparian and waterway health | Length (km) of stream bed stabilised | Number of structures |  |  | OG2.3 | On-ground | Native vegetation protected by fencing | Area (ha) of riparian native vegetation protected by fencing | Streambank length (km) of riparian vegetation protected
| SA | Mount Lofty Ranges | [7 empty] | 42 | On-ground activities | Riparian and waterway health | Number of off-stream (alternative) watering sites installed | Not applicable |  |  | OG2.4 | On-ground | Native vegetation protected by fencing | Area (ha) of terrestrial native vegetation protected by fencing | -
| SA | Northern and Yorke Agricultural District | [7 empty] | 43 | On-ground activities | Riparian and waterway health | Length of in-stream habitat established | Number of large woody debris |  |  | OG3.1 | On-ground | Native vegetation enhanced/rehabilitated (include improved fire management practice under this category) | Area (ha) of coastal native vegetation enhanced/rehabilitated | -
| SA | Arid Lands | [7 empty] | 44 | On-ground activities | Riparian and waterway health | Number of fish barriers addressed | Not applicable |  |  | OG3.2 | On-ground | Native vegetation enhanced/rehabilitated (include improved fire management practice under this category) | Area (ha) of wetland native vegetation enhanced/rehabilitated | -
| SA | SA Murray Darling Basin | [7 empty] | 45 | On-ground activities | Riparian and waterway health | Length (km) of stream opened up to fish passage | Not applicable |  |  | OG3.3 | On-ground | Native vegetation enhanced/rehabilitated (include improved fire management practice under this category) | Area (ha) of riparian native vegetation enhanced/rehabilitated | Streambank length (km) of riparian vegetation enhanced/rehabilitated
| SA | South East | [7 empty] | 46 | On-ground activities | Riparian and waterway health | Number of off-river stock watering points established | Not applicable |  |  | OG3.4 | On-ground | Native vegetation enhanced/rehabilitated (include improved fire management practice under this category) | Area (ha) of terrestrial native vegetation enhanced/rehabilitated | -
| TAS | North Tasmania | [7 empty] | 47 | On-ground activities | Wetlands health protected or enhanced | Area (hectares) of wetland protected | Not applicable |  |  | OG4.1 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) of native plantation established | Area (ha) of this vegetation that are locally occurring natives
| TAS | North West | [7 empty] | 48 | On-ground activities | Wetlands health protected or enhanced | Area (hectares) of wetland enhanced/rehabilitated | Not applicable |  |  | OG4.2 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) planted to coastal native species | Area (ha) of this vegetation that are locally occurring natives
| TAS | South Tasmania | [7 empty] | 49 | On-ground activities | Wetlands health protected or enhanced | Area (hectares) of wetlands with reinstated connectivity | Not applicable |  |  | OG4.3 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) planted to wetland native species | Area (ha) of this vegetation that are locally occurring natives
| TAS | Tasmanian NAP Region | [7 empty] | 50 | On-ground activities | Management of significant species or ecological communities | Area (hectares) of habitat management | Not applicable |  |  | OG4.4 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) planted to riparian native species | Area (ha) of this vegetation that are locally occurring natives
| VIC | Corangamite | [7 empty] | 51 | On-ground activities | Management of significant species or ecological communities | Area (hectares) protected by fencing specifically for significant species/community protection | Not applicable |  |  | OG4.5 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Stream bank length (km) of riparian vegetation enhanced/rehabilitated | -
| VIC | East Gippsland | [7 empty] | 52 | On-ground activities | Management of significant species or ecological communities | Number of individuals translocated or established | Not applicable |  |  | OG4.6 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) planted to terrestrial native species | Area (ha) of this vegetation that are locally occurring natives
| VIC | Glenelg Hopkins | [7 empty] | 53 | On-ground activities | Management of significant species or ecological communities | Number of successful individuals bred through an established breeding program | Not applicable |  |  | OG5.1 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic plantation established | -
| VIC | Goulburn Broken | [7 empty] | 54 | On-ground activities | Management of significant species or ecological communities | Number of seedbanks managed | Weight (kg) of seeds collected |  |  | OG5.2 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic vegetation established | -
| VIC | Mallee | [7 empty] | 55 | On-ground activities | Significant pest plant control | Area (hectares) of pest plant control | Type of pest plant (e.g. blackberry, boxthorn etc) |  |  | OG5.3 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic perennial pastures established | -
| VIC | North Central | [7 empty] | 56 | On-ground activities | Significant pest vertebrate control | Area (hectares) of pest animal control | Type of pest animal (e.g.rabbits, foxes) |  |  | OG5.4 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic, non-perennial special purpose pastures established | -
| VIC | North East | [7 empty] | 57 | On-ground activities | Soil management | Area (hectares) of land treated for soil erosion through engineering works | Number of sites |  |  | OG6.1 | On-ground | Wetlands health protected or enhanced | Area (ha) of wetlands with connectivity reinstated | -
| VIC | Port Phillip | [7 empty] | 58 | On-ground activities | Soil management | Area (hectares) of land treated for soil erosion through exclusion fencing | Number of sites |  |  | OG7.1 | On-ground | Management of significant species or ecological communities | Area (ha) protected by fencing specifically for significant species/ ecological community protection | -
| VIC | West Gippsland | [7 empty] | 59 | On-ground activities | Soil management | Area (hectares) of treatment for acid sulfate soils | Not applicable |  |  | OG7.2 | On-ground | Management of significant species or ecological communities | Number of breeding programs developed | Number of individuals bred
| VIC | Wimmera | [7 empty] | 60 | On-ground activities | Soil management | Area (hectares) of soil treatment for other than erosion, salinity or acid sulfate soils | Not applicable |  |  | OG7.3 | On-ground | Management of significant species or ecological communities | Number of translocation programs developed | Number of individuals translocated or established
| WA | Avon | [7 empty] | 61 | On-ground activities | Salinity control measures | Area (hectares) of land treated for rising groundwater through surface drainage | Length (km) of drain |  |  | OG7.4 | On-ground | Management of significant species or ecological communities | Number of seedbanks developed | -
| WA | Northern Agricultural | [7 empty] | 62 | On-ground activities | Salinity control measures | Area (hectares) of land treated for rising groundwater through sub-surface drainage | Length (km) of drain |  |  | OG8.1 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest plant control measures implemented | -
| WA | Rangelands | [7 empty] | 63 | On-ground activities | Salinity control measures | Area (hectares) of land treated for rising groundwater through groundwater pumping | Not applicable |  |  | OG8.2 | On-ground | Significant pest plant, animal and disease control | Number of weed seed wash down facilities established or renovated | -
| WA | South Coast | [7 empty] | 64 | On-ground activities | Salinity control measures | Area (hectares) of land treated by salt evaporation ponds | Not applicable |  |  | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | -
| WA | South West | [7 empty] | 65 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by sewage plant | Number of sewage plants |  |  | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | -
| WA | Swan | [7 empty] | 66 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by sewage plant | Number of sewage plants |  |  | OG8.5 | On-ground | Significant pest plant, animal and disease control | Area (ha) of plant disease control measures implemented | -
[10 empty] | 67 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by human effluent disposal other than sewage plant | Number of human effluent disposal sites other than sewage plant |  |  | OG9.1 | On-ground | Works related to soil management and other soil treatments | Area (ha) of land treated and/ or protected from soil erosion by engineering works | -
[10 empty] | 68 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by human effluent disposal other than sewage plant | Number of human effluent disposal sites other than sewage plant |  |  | OG9.2 | On-ground | Works related to soil management and other soil treatments | Area (ha) of land treated for soil erosion through exclusion fencing | -
[10 empty] | 69 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by dairy effluent control measures | Number of properties with dairy effluent control measures |  |  | OG9.3 | On-ground | Works related to soil management and other soil treatments | Area (ha) of acid sulphate soils identified and treated/protected | -
[10 empty] | 70 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by dairy effluent control measures | Number of properties with dairy effluent control measures |  |  | OG9.4 | On-ground | Works related to soil management and other soil treatments | Area (ha) of soil treatment for other than erosion or acid sulphate soils | -
[10 empty] | 71 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by feedlot effluent control works | Number of properties with feedlot effluent control works |  |  | P1.1 | Planning | Improved codes of practice or guidelines | Number of best management practice codes or guidelines completed | -
[10 empty] | 72 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by feedlot effluent control works | Number of properties with feedlot effluent control works |  |  | P2.1 | Planning | Regional plans | Number of regional strategies or investment plans accredited | -
[10 empty] | 73 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by other effluent control works | Number of properties with other effluent control works |  |  | P2.2 | Planning | Regional plans | Number of regional strategies or investment plans reviewed or revised | -
[10 empty] | 74 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by other effluent control works | Number of properties with other effluent control works |  |  | P3.1 | Planning | Sub-regional plans | Number of catchment or sub-catchment plans or strategies completed | -
[10 empty] | 75 | On-ground activities | Water contaminant management | Number of stormwater quality control devices | Number of constructed wetlands |  |  | P3.2 | Planning | Sub-regional plans | Number of property or reserve management plans completed | -
[10 empty] | 76 | On-ground activities | Water contaminant management | Number of new stormwater reuse systems added | Not applicable |  |  | P4.1 | Planning | Resource management plans | Number of recovery or management plans for threatened species or ecological communities completed | Number of species or communities covered by the plan
[10 empty] | 77 | On-ground activities | Water use efficiency | Area (hectares) of land using improved irrigation practices | Number of land managers using improved irrigation practices |  |  | P4.2 | Planning | Resource management plans | Number of other resource management plans completed | -
[10 empty] | 78 | On-ground activities | Water use efficiency | Volume (ML) of water saved | Number of on-farms reuse systems |  |  | P5.1 | Planning | Other plans | Number of other biophysical, economic or socially related plans completed | -
[10 empty] | 79 | On-ground activities | Water use efficiency | Volume (ML) of water saved | Number of land managers using on-farm water saving practice by drainage diversion |  |  | RA1.1 | Resource assessment | Setting or monitoring resource condition targets | Number of studies completed | Number of sites monitored
[10 empty] | 80 | On-ground activities | Water use efficiency | Volume (ML) of water saved using off-farm water mechanisms | Length (km) of channel improved or piped if applicable |  |  | RA1.2 | Resource assessment | Setting or monitoring resource condition targets | Number of new monitoring programs established | -
[10 empty] | 81 | On-ground activities | Bore capping | Number of groundwater bores capped | Not applicable |  |  | RA1.3 | Resource assessment | Setting or monitoring resource condition targets | Number of existing monitoring programs enhanced | -
[10 empty] | 82 | Planning | Improved practice codes or guidelines | Number of best management practice codes developed | Not applicable |  |  | RA2.1 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of biophysical studies completed | Area (ha) surveyed
[10 empty] | 83 | Planning | Improved practice codes or guidelines | Number of best management practice guidelines developed | Not applicable |  |  | RA2.2 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of social /economic studies completed | Size of population covered by the survey sample
[10 empty] | 84 | Planning | Integrated catchment or sub-catchment plans | Number of catchment plans developed | Not applicable |  |  | RA2.3 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of reports completed | -
[10 empty] | 85 | Planning | Integrated catchment or sub-catchment plans | Number of sub-catchment plans developed | Not applicable |  |  | RA3.1 | Resource assessment | Decision support tools | Number of models developed | -
[10 empty] | 86 | Planning | Property management plans | Number of property management plans completed | Not applicable |  |  | RA3.2 | Resource assessment | Decision support tools | Number of information management systems developed | -
[10 empty] | 87 | Planning | Species recovery plans and action statements | Number of endangered species recovery plans developed | Not applicable |  |  | RA3.3 | Resource assessment | Decision support tools | Number of other decision support tools developed | -
[10 empty] | 88 | Planning | Species recovery plans and action statements | Number of endangered species action statements developed | Not applicable |  |  | RA4.1 | Resource assessment | Research and development studies | Number of research and development studies completed | -
[10 empty] | 89 | Resource assessment | Baseline, trend or condition studies for targets | Number of studies | Not applicable
[10 empty] | 90 | Resource assessment | Baseline, trend or condition studies for targets | Number of sites monitored | Not applicable
[10 empty] | 91 | Resource assessment | Decision support tools | Number of models developed | Not applicable
[10 empty] | 92 | Resource assessment | Decision support tools | Number of information management systems developed | Not applicable
[10 empty] | 93 | Resource assessment | Decision support tools | Number of other decision support tools developed | Not applicable
[10 empty] | 94 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of vegetation studies | Area (hectares) surveyed
[10 empty] | 95 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of salinity studies | Area (hectares) surveyed
[10 empty] | 96 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of species studies | Area (hectares) surveyed
[10 empty] | 97 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of soil studies | Area (hectares) surveyed
[10 empty] | 98 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of marine studies | Area (hectares) surveyed
[10 empty] | 99 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of groundwater studies | Area (hectares) surveyed
[10 empty] | 100 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of surface water / inland aquatic studies | Area (hectares) surveyed
[10 empty] | 101 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of social studies | Area (hectares) surveyed
[10 empty] | 102 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of other studies | Area (hectares) surveyed
[10 empty] | 103 | Resource assessment | Research and development studies | Number of research and development studies undertaken | Not applicable
[10 empty] | 401 | Capacity building | Information and Knowledge Infrastructure | Instances of significant growth in/increased access to info technology capacity | Not applicable
[10 empty] | 402 | Capacity building | Information and Knowledge Infrastructure | Activity in knowledge evaluation (science/technical panels, board activity, critical workshops) | Not applicable
[10 empty] | 403 | Capacity building | Relationship and Organisational Development | Number of documented collaborative arrangements (MOUs, joint projects, data sharing arrangements) | Not applicable
[10 empty] | 404 | Capacity building | Relationship and Organisational Development | Number of organisations involved in collaborative negotiations towards improved relationships | Not applicable
[10 empty] | 405 | Capacity building | Relationship and Organisational Development | Number of organisational development or learning reviews (performance reviews, capacity building, planning, logic analyses, evaluation processes) | Not applicable
[10 empty] | 406 | Institutional Establishment/Maintenance | Project Development/Leveraging Investment | Number of program types for which projects and proposals were developed | Not applicable
[10 empty] | 407 | Institutional Establishment/Maintenance | Organisational Establishment or Operations | Number of necessary business documents produced (constitution, business plan) | Not applicable
[10 empty] | 408 | Institutional Establishment/Maintenance | Office administration, HR | Expenditure ($) on hiring, securing premises and development of PDs | Not applicable

## Output Map
Output_Code | Old Code | Output Type | Standard Output | Output Unit of Measure #1 | Output Unit of Measure #2 | Output Unit of Measure #2 - Grouped | Output_Code | Output_Type | Standard_Output | Output_Unit_of_Measure_1# | Output_Unit_of_Measure_2# | Output_Description
[7 empty] | 401 | Capacity building | Information and Knowledge Infrastructure | Instances of significant growth in/increased access to info technology capacity | -
[7 empty] | 402 | Capacity building | Information and Knowledge Infrastructure | Activity in knowledge evaluation (science/technical panels, board activity, critical workshops) | -
[7 empty] | 403 | Capacity building | Relationship and Organisational Development | Number of documented collaborative arrangements (MOUs, joint projects, data sharing arrangements) | -
[7 empty] | 404 | Capacity building | Relationship and Organisational Development | Number of organisations involved in collaborative negotiations towards improved relationships | -
[7 empty] | 405 | Capacity building | Relationship and Organisational Development | Number of organisational development or learning reviews (performance reviews, capacity building, planning, logic analyses, evaluation processes) | -
[7 empty] | 406 | Institutional Establishment/Maintenance | Project Development/Leveraging Investment | Number of program types for which projects and proposals were developed | Not applicable
[7 empty] | 407 | Institutional Establishment/Maintenance | Organisational Establishment or Operations | Number of necessary business documents produced (constitution, business plan) | Not applicable
[7 empty] | 408 | Institutional Establishment/Maintenance | Office administration, HR | Expenditure ($) on hiring, securing premises and development of PDs | Not applicable
CB1.1 | 1 | Capacity building | Awareness raising activities | Number of demonstrations | Number of participants in person-days | Number of participants at demonstrations in person-days | CB1.1 | Capacity building | Awareness raising | Number of awareness raising events such as demonstrations, field days or study tours conducted | Number of participants in person-days | An awareness-raising event is an event designed to pass on information and improve knowledge and understanding. To calculate person-days, multiply the number of participants by the amount of a day or days the event ran for (use only half day or full day units) and round totals to the nearest whole number
CB1.1 | 2 | Capacity building | Awareness raising activities | Number of field days | Number of participants in person-days | Number of participants at field days in person-days | CB1.1 | Capacity building | Awareness raising | Number of awareness raising events such as demonstrations, field days or study tours conducted | Number of participants in person-days | An awareness-raising event is an event designed to pass on information and improve knowledge and understanding. To calculate person-days, multiply the number of participants by the amount of a day or days the event ran for (use only half day or full day units) and round totals to the nearest whole number
CB1.1 | 3 | Capacity building | Awareness raising activities | Number of study tours | Number of participants in person-days | Number of participants on study tours in person-days | CB1.1 | Capacity building | Awareness raising | Number of awareness raising events such as demonstrations, field days or study tours conducted | Number of participants in person-days | An awareness-raising event is an event designed to pass on information and improve knowledge and understanding. To calculate person-days, multiply the number of participants by the amount of a day or days the event ran for (use only half day or full day units) and round totals to the nearest whole number
CB1.1 | 4 | Capacity building | Awareness raising activities | Number of other non-training forums | Number of participants in person-days | Number of participants at other non-training forums in person-days | CB1.1 | Capacity building | Awareness raising | Number of awareness raising events such as demonstrations, field days or study tours conducted | Number of participants in person-days | An awareness-raising event is an event designed to pass on information and improve knowledge and understanding. To calculate person-days, multiply the number of participants by the amount of a day or days the event ran for (use only half day or full day units) and round totals to the nearest whole number
CB1.2 | 5 | Capacity building | Awareness raising activities | Number of brochures developed | Quantity distributed | Quantity of brochures distributed | CB1.2 | Capacity building | Awareness raising | Number of written products such as brochures, newsletters, posters or fact sheets developed | Estimated number of recipients | Includes less formal written material such as brochures, newsletters, posters and fact sheets. Formal documents such as reports and plans should be reported under CB3.1 or the Planning or Resource Assessment categories
CB1.2 | 6 | Capacity building | Awareness raising activities | Number of newsletters developed | Quantity distributed | Quantity of newsletters distributed | CB1.2 | Capacity building | Awareness raising | Number of written products such as brochures, newsletters, posters or fact sheets developed | Estimated number of recipients | Includes less formal written material such as brochures, newsletters, posters and fact sheets. Formal documents such as reports and plans should be reported under CB3.1 or the Planning or Resource Assessment categories
CB1.2 | 8 | Capacity building | Awareness raising activities | Number of other non-training products or materials developed | Quantity distributed | Quantity of other non-training products or materials distributed | CB1.2 | Capacity building | Awareness raising | Number of written products such as brochures, newsletters, posters or fact sheets developed | Estimated number of recipients | Includes less formal written material such as brochures, newsletters, posters and fact sheets. Formal documents such as reports and plans should be reported under CB3.1 or the Planning or Resource Assessment categories
CB1.3 | 7 | Capacity building | Awareness raising activities | Number of displays developed | Quantity distributed | Quantity of displays distributed | CB1.3 | Capacity building | Awareness raising | Number of displays for use at events such as regional meetings developed | - | Covers displays developed for use at events such as regional meetings, agricultural shows or other community events
CB1.4 | 9 | Capacity building | Awareness raising activities | Number of media opportunities | Not applicable | Not applicable | CB1.4 | Capacity building | Awareness raising | Number of media opportunities resulting in articles in newspapers or on radio or television created | - | Includes articles in newspapers and magazines, items on radio or in television programs
CB1.5 | 10 | Capacity building | Awareness raising activities | Number of websites developed | Not applicable | Not applicable | CB1.5 | Capacity building | Awareness raising | Number of websites developed or significantly enhanced | - | Websites developed to provide information related to regional natural resource management
CB2.1 | 13 | Capacity building | Skills and training activities | Number of training sessions held | Number of participants in person-days | Number of participants at training sessions in person-days | CB2.1 | Capacity building | Skills and training | Number of training sessions, workshops, seminars or other skills and training events conducted | Number of participants in person-days | Structured activities designed to improve existing skills or develop new ones. Training sessions MAY lead to or contribute to formal qualifications like a TAFE certificate but need not necessarily do so. To calculate person-days see CB1.1
CB2.1 | 14 | Capacity building | Skills and training activities | Number of workshops held | Number of participants in person-days | Number of participants at workshops in person-days | CB2.1 | Capacity building | Skills and training | Number of training sessions, workshops, seminars or other skills and training events conducted | Number of participants in person-days | Structured activities designed to improve existing skills or develop new ones. Training sessions MAY lead to or contribute to formal qualifications like a TAFE certificate but need not necessarily do so. To calculate person-days see CB1.1
CB2.1 | 15 | Capacity building | Skills and training activities | Number of seminars held | Number of participants in person-days | Number of participants at seminars in person-days | CB2.1 | Capacity building | Skills and training | Number of training sessions, workshops, seminars or other skills and training events conducted | Number of participants in person-days | Structured activities designed to improve existing skills or develop new ones. Training sessions MAY lead to or contribute to formal qualifications like a TAFE certificate but need not necessarily do so. To calculate person-days see CB1.1
CB2.1 | 16 | Capacity building | Skills and training activities | Number of other skills and training events held | Number of participants in person-days | Number of participants at other skills and training events in person-days | CB2.1 | Capacity building | Skills and training | Number of training sessions, workshops, seminars or other skills and training events conducted | Number of participants in person-days | Structured activities designed to improve existing skills or develop new ones. Training sessions MAY lead to or contribute to formal qualifications like a TAFE certificate but need not necessarily do so. To calculate person-days see CB1.1
CB2.2 | 17 | Capacity building | Skills and training activities | Number of workbooks developed | Quantity distributed | Quantity of workbooks distributed | CB2.2 | Capacity building | Skills and training | Number of workbooks, course notes or other key materials developed | Quantity distributed | Use CB2.2 when materials are developed to be used by others or for training events to be run by your project in a future reporting period. If developed for a event you’re currently running, use CB2.1
CB2.2 | 18 | Capacity building | Skills and training activities | Number of course notes developed | Quantity distributed | Quantity of course notes distributed | CB2.2 | Capacity building | Skills and training | Number of workbooks, course notes or other key materials developed | Quantity distributed | Use CB2.2 when materials are developed to be used by others or for training events to be run by your project in a future reporting period. If developed for a event you’re currently running, use CB2.1
CB2.2 | 19 | Capacity building | Skills and training activities | Number of other key materials developed | Quantity distributed | Quantity of other key materials distributed | CB2.2 | Capacity building | Skills and training | Number of workbooks, course notes or other key materials developed | Quantity distributed | Use CB2.2 when materials are developed to be used by others or for training events to be run by your project in a future reporting period. If developed for a event you’re currently running, use CB2.1
CB3.1 | 83 | Planning | Improved practice codes or guidelines | Number of best management practice guidelines developed | Not applicable | Not applicable | CB3.1 | Capacity building | Establishing new institutional arrangements | Number of key organisational documents produced | - | Include only major documents required to establish an organisation or business process such as a constitution, business plan, strategic plan, implementation/ operational plan, policy and procedures manual, reporting templates etc
CB3.2 | 83 | Planning | Improved practice codes or guidelines | Number of best management practice guidelines developed | Not applicable | Not applicable | CB3.2 | Capacity building | Establishing new institutional arrangements | Number of formally documented collaborative arrangements developed | - | Includes written agreements such as MOUs, joint project undertakings, data sharing agreements etc
CB3.3 | 83 | Planning | Improved practice codes or guidelines | Number of best management practice guidelines developed | Not applicable | Not applicable | CB3.3 | Capacity building | Establishing new institutional arrangements | Number of arrangements for effective collaboration negotiated where a formal agreement does not exist | - | Include only significant negotiations for cooperation or collaboration with new potential partners. This is a similar output to CB3.2 but applies where the agreement is not formally documented
CB4.1 | 92 | Resource assessment | Decision support tools | Number of information management systems developed | Not applicable | Not applicable | CB4.1 | Capacity building | Organisational learning | Number of governance tools developed | - | Eg. decision-support tools for developing investment priorities
CB4.2 | 102 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of other studies | Area (hectares) surveyed | Area (hectares) surveyed by other studies | CB4.2 | Capacity building | Organisational learning | Number of significant knowledge evaluation events held | - | Includes Science or Technical Panel assessment of targets, community or Board prioritisation workshops, other critical workshops etc
CB4.3 | 102 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of other studies | Area (hectares) surveyed | Area (hectares) surveyed by other studies | CB4.3 | Capacity building | Organisational learning | Number of organisational learning reviews completed | - | Eg. reviews/ studies, significant evaluation processes
CB4.4 | 92 | Resource assessment | Decision support tools | Number of information management systems developed | Not applicable | Not applicable | CB4.4 | Capacity building | Organisational learning | Number new databases developed | - | Include stakeholder databases, consultant or product supply databases and other organisational management databases. See RA3.2 for larger information systems related to Resource Assessment
CB5.1 | 12 | Capacity building | Facilitation motivation and support activities | Number of community groups or community projects assisted | Not applicable | Not applicable | CB5.1 | Capacity building | Community Support | Number of community groups OR projects assisted | - | Refers to facilitation and type activities. Facilitators can report the number of groups or projects they have assisted in each six month period (however, when reporting an annual total each group or project should only be counted once)
CB5.2 | 11 | Capacity building | Facilitation motivation and support activities | Number of FTE active community support positions (facilitators or coordinators) | Not applicable | Not applicable | CB5.2 | Capacity building | Community Support | Number of FTE active community support positions (facilitators or coordinators) | - | Number of facilitators or coordinators positions funded through the project
OG1.1 | 20 | On-ground activities | Conservation by agreements | Number of legal conservation covenants and other legal agreements | Area (hectares) covered | Area (hectares) of legal conservation covenants and other legal agreements covered | OG1.1 | On-ground | Conservation by agreements | Number of conservation covenants or other agreements attached to title negotiated | Area (ha) protected | Legal agreements would normally be attached to the title of land. Negotiated means to the formal agreement stage
OG1.2 | 21 | On-ground activities | Conservation by agreements | Number of voluntary conservation agreements | Area (hectares) covered | Area (hectares) of voluntary conservation agreements covered | OG1.2 | On-ground | Conservation by agreements | Number of voluntary conservation agreements negotiated | Area (ha) protected | Voluntary agreements are not attached to title of the land. Negotiated means to the formal agreement stage
OG10.1 | 61 | On-ground activities | Salinity control measures | Area (hectares) of land treated for rising groundwater through surface drainage | Length (km) of drain | Length (km) of surface drain | OG10.1 | On-ground | Works related to the improved management of surface or groundwater | Area (ha) of land treated through surface drainage | Length (km) of drain | -
OG10.2 | 62 | On-ground activities | Salinity control measures | Area (hectares) of land treated for rising groundwater through sub-surface drainage | Length (km) of drain | Length (km) of sub-surface drain | OG10.2 | On-ground | Works related to the improved management of surface or groundwater | Area (ha) of land treated through sub-surface drainage | Length (km) of drain | -
OG10.3 | 62 | On-ground activities | Salinity control measures | Area (hectares) of land treated for rising groundwater through sub-surface drainage | Length (km) of drain | Length (km) of sub-surface drain | OG10.3 | On-ground | Works related to the improved management of surface or groundwater | Area (ha) of land treated through improvements to existing drainage systems | Length (km) of drain improved | -
OG10.4 | 63 | On-ground activities | Salinity control measures | Area (hectares) of land treated for rising groundwater through groundwater pumping | Not applicable | Not applicable | OG10.4 | On-ground | Works related to the improved management of surface or groundwater | Area (ha) of land treated for rising groundwater through groundwater pumping | - | -
OG11.1 | 40 | On-ground activities | Riparian and waterway health | Length (km) of stream bank stabilised | Number of structures | Number of stream bank structures installed | OG11.1 | On-ground | Works for improving waterway health | Length (m) of stream bank stabilised with engineering works | - | For engineering approaches eg use of gabions only. Where banks have been stabilised with vegetation use OG4.4. Include development of properly constructed stock crossings and stock access points. Count both sides of a stream if applicable. For example, stabilising the banks on each side of a one-kilometre length of stream would mean two kilometres of bank have been stabilised.
OG11.2 | 41 | On-ground activities | Riparian and waterway health | Length (km) of stream bed stabilised | Number of structures | Number of stream bed structures installed | OG11.2 | On-ground | Works for improving waterway health | Length (m) of stream bed stabilised | - | -
OG11.3 | 42 | On-ground activities | Riparian and waterway health | Number of off-stream (alternative) watering sites installed | Not applicable | Not applicable | OG11.3 | On-ground | Works for improving waterway health | Number of off-stream (alternative) watering sites installed | Length (km) of stream bank protected from stock | If you have erected fencing to exclude stock from a waterway and by doing so have protected some native vegetation, record the amount of vegetation protected under OG2.3
OG11.4 | 43 | On-ground activities | Riparian and waterway health | Length of in-stream habitat established | Number of large woody debris | Number of large woody debris installed | OG11.4 | On-ground | Works for improving waterway health | Length (kilometres) of in-stream habitat established | - | -
OG11.5 | 44 | On-ground activities | Riparian and waterway health | Number of fish barriers addressed | Not applicable | Not applicable | OG11.5 | On-ground | Works for improving waterway health | Number of fish barriers modified and/ or removed | - | Where modification significantly reduces barrier to fish passage
OG11.5 | 45 | On-ground activities | Riparian and waterway health | Length (km) of stream opened up to fish passage | Not applicable | Not applicable | OG11.5 | On-ground | Works for improving waterway health | Number of fish barriers modified and/ or removed | - | Where modification significantly reduces barrier to fish passage
OG12.1 | 65 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by sewage plant | Number of sewage plants | Number of sewage plants | OG12.1 | On-ground | Works for improving water quality | Number of new sewage plants constructed | Volume (ML) of effluent removed or contained by sewage plant | Effluent removed or contained can include effluent re-used when in accordance with best management practice
OG12.1 | 66 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by sewage plant | Number of sewage plants | Number of sewage plants | OG12.1 | On-ground | Works for improving water quality | Number of new sewage plants constructed | Volume (ML) of effluent removed or contained by sewage plant | Effluent removed or contained can include effluent re-used when in accordance with best management practice
OG12.2 | 65 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by sewage plant | Number of sewage plants | Number of sewage plants | OG12.2 | On-ground | Works for improving water quality | Number of sewage plants improved with better treatment processes | Volume (ML) of effluent removed or contained by sewage plant | Effluent removed or contained can include effluent re-used when in accordance with best management practice
OG12.2 | 66 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by sewage plant | Number of sewage plants | Number of sewage plants | OG12.2 | On-ground | Works for improving water quality | Number of sewage plants improved with better treatment processes | Volume (ML) of effluent removed or contained by sewage plant | Effluent removed or contained can include effluent re-used when in accordance with best management practice
OG12.3 | 67 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by human effluent disposal other than sewage plant | Number of human effluent disposal sites other than sewage plant | Number of human effluent disposal sites other than sewage plant | OG12.3 | On-ground | Works for improving water quality | Number of human effluent disposal sites other than sewage plant constructed | Volume (ML) of effluent removed or contained by effluent control works | Includes facilities installed for the emptying of holding tanks on boats to prevent discharge of sewage to waterways
OG12.3 | 68 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by human effluent disposal other than sewage plant | Number of human effluent disposal sites other than sewage plant | Number of human effluent disposal sites other than sewage plant | OG12.3 | On-ground | Works for improving water quality | Number of human effluent disposal sites other than sewage plant constructed | Volume (ML) of effluent removed or contained by effluent control works | Includes facilities installed for the emptying of holding tanks on boats to prevent discharge of sewage to waterways
OG12.4 | 69 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by dairy effluent control measures | Number of properties with dairy effluent control measures | Number of properties with dairy effluent control measures | OG12.4 | On-ground | Works for improving water quality | Number of effluent control works for animal waste established on properties | Volume (ML) of effluent removed or contained by effluent control works | Includes dairies, feedlots, piggeries and chicken farms
OG12.4 | 70 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by dairy effluent control measures | Number of properties with dairy effluent control measures | Number of properties with dairy effluent control measures | OG12.4 | On-ground | Works for improving water quality | Number of effluent control works for animal waste established on properties | Volume (ML) of effluent removed or contained by effluent control works | Includes dairies, feedlots, piggeries and chicken farms
OG12.4 | 71 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by feedlot effluent control works | Number of properties with feedlot effluent control works | Number of properties with feedlot effluent control works | OG12.4 | On-ground | Works for improving water quality | Number of effluent control works for animal waste established on properties | Volume (ML) of effluent removed or contained by effluent control works | Includes dairies, feedlots, piggeries and chicken farms
OG12.4 | 72 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by feedlot effluent control works | Number of properties with feedlot effluent control works | Number of properties with feedlot effluent control works | OG12.4 | On-ground | Works for improving water quality | Number of effluent control works for animal waste established on properties | Volume (ML) of effluent removed or contained by effluent control works | Includes dairies, feedlots, piggeries and chicken farms
OG12.4 | 73 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by other effluent control works | Number of properties with other effluent control works | Number of properties with other effluent control works | OG12.4 | On-ground | Works for improving water quality | Number of effluent control works for animal waste established on properties | Volume (ML) of effluent removed or contained by effluent control works | Includes dairies, feedlots, piggeries and chicken farms
OG12.4 | 74 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by other effluent control works | Number of properties with other effluent control works | Number of properties with other effluent control works | OG12.4 | On-ground | Works for improving water quality | Number of effluent control works for animal waste established on properties | Volume (ML) of effluent removed or contained by effluent control works | Includes dairies, feedlots, piggeries and chicken farms
OG12.5 | 73 | On-ground activities | Water contaminant management | Volume (ML) of effluent removed or contained by other effluent control works | Number of properties with other effluent control works | Number of properties with other effluent control works | OG12.5 | On-ground | Works for improving water quality | Number of other effluent or farm runoff control works established on properties | Volume (ML) of effluent removed or contained by effluent control works | Includes activities to prevent pesticide and nutrient runoff
OG12.5 | 74 | On-ground activities | Water contaminant management | Amount (tonnes) of effluent removed or contained by other effluent control works | Number of properties with other effluent control works | Number of properties with other effluent control works | OG12.5 | On-ground | Works for improving water quality | Number of other effluent or farm runoff control works established on properties | Volume (ML) of effluent removed or contained by effluent control works | Includes activities to prevent pesticide and nutrient runoff
OG12.6 | 75 | On-ground activities | Water contaminant management | Number of stormwater quality control devices | Number of constructed wetlands | Number of constructed wetlands | OG12.6 | On-ground | Works for improving water quality | Number of stormwater quality control devices constructed | Kg of material prevented from entering waterway per years | The amount of material prevented from entering waterways would be the amount collected by the type of device used
OG12.7 | 75 | On-ground activities | Water contaminant management | Number of stormwater quality control devices | Number of constructed wetlands | Number of constructed wetlands | OG12.7 | On-ground | Works for improving water quality | Number of constructed wetlands | Area of constructed wetlands | -
OG13.1 | 77 | On-ground activities | Water use efficiency | Area (hectares) of land using improved irrigation practices | Number of land managers using improved irrigation practices | Number of land managers using improved irrigation practices | OG13.1 | On-ground | Works related to improving water use efficiency | Area (ha) of land where improved irrigation practices have been adopted | Number of land managers using improved irrigation practices | -
OG13.2 | 78 | On-ground activities | Water use efficiency | Volume (ML) of water saved | Number of on-farms reuse systems | Number of on-farms reuse systems | OG13.2 | On-ground | Works related to improving water use efficiency | Number of on-farms reuse systems constructed | Volume (ML) of water saved per year | -
OG13.3 | 79 | On-ground activities | Water use efficiency | Volume (ML) of water saved | Number of land managers using on-farm water saving practice by drainage diversion | Number of land managers using on-farm water saving practice by drainage diversion | OG13.3 | On-ground | Works related to improving water use efficiency | Number of land managers who have adopted on-farm water saving practice by drainage diversion | Volume (ML) of water saved per year | -
OG13.4 | 80 | On-ground activities | Water use efficiency | Volume (ML) of water saved using off-farm water mechanisms | Length (km) of channel improved or piped if applicable | Length (km) of channel improved or piped | OG13.4 | On-ground | Works related to improving water use efficiency | Length (km) of channel improved or piped if applicable | Volume (ML) of water saved per year | -
OG13.5 | 81 | On-ground activities | Bore capping | Number of groundwater bores capped | Not applicable | Not applicable | OG13.5 | On-ground | Works related to improving water use efficiency | Number of groundwater bores capped | Volume (ML) of water saved per year | -
OG13.6 | 76 | On-ground activities | Water contaminant management | Number of new stormwater reuse systems added | Not applicable | Not applicable | OG13.6 | On-ground | Works related to improving water use efficiency | Number of new stormwater reuse systems | Volume (ML) of water saved per year | -
OG2.1 | 23 | On-ground activities | Indigenous vegetation protected by fencing | Area (hectares) of coastal indigenous vegetation protected by fencing | Not applicable | Not applicable | OG2.1 | On-ground | Native vegetation protected by fencing | Area (ha) of coastal native vegetation protected by fencing | - | Coastal land is defined as land that is either within one kilometre: (a) landward of the open coast high water mark; or (b) around all bays, estuaries, coastal lakes, lagoons or islands; and tidal waters of coastal rivers to the limit of mangroves or the tidal limit whichever is closer to the sea. [Adapted from NSW coastal policy]. Native vegetation is any vegetation species that existed before European settlement including trees, saplings, shrubs, scrub, understorey, groundcover or plants in a wetland [Adapted from the Native Vegetation Act 2003]
OG2.2 | 47 | On-ground activities | Wetlands health protected or enhanced | Area (hectares) of wetland protected | Not applicable | Not applicable | OG2.2 | On-ground | Native vegetation protected by fencing | Area (ha) of wetland native vegetation protected by fencing | - | Wetland is defined as land where “an excess of water is the dominant factor determining the nature of soil development and the types of plant and animal communities living at the soil surface” [Definition taken from DEH website] See above for definition of ‘native’
OG2.3 | 24 | On-ground activities | Indigenous vegetation protected by fencing | Area (hectares) of riparian indigenous vegetation protected by fencing | Streambank length (km) of riparian vegetation protected | Streambank length (km) of riparian indigenous vegetation protected by fencing | OG2.3 | On-ground | Native vegetation protected by fencing | Area (ha) of riparian native vegetation protected by fencing | Streambank length (km) of riparian vegetation protected | Measure both sides of the stream bank. Riparian land is defined as “any land which adjoins, directly influences’ or is influenced by a body of water”. [Land and Water Australia] See above for definition of ‘native’. Measure both sides of the stream bank, if applicable
OG2.4 | 22 | On-ground activities | Indigenous vegetation protected by fencing | Area (hectares) of terrestrial indigenous vegetation protected by fencing | Not applicable | Not applicable | OG2.4 | On-ground | Native vegetation protected by fencing | Area (ha) of terrestrial native vegetation protected by fencing | - | Terrestrial is defined as any land not included in the above three categories. See above for definition of ‘native’
OG3.1 | 26 | On-ground activities | Indigenous vegetation enhanced/rehabilitated | Area (hectares) of coastal indigenous vegetation enhanced/rehabilitated | Not applicable | Not applicable | OG3.1 | On-ground | Native vegetation enhanced/rehabilitated (include improved fire management practice under this category) | Area (ha) of coastal native vegetation enhanced/rehabilitated | - | See above for definition of ‘coastal’ and ‘native’
OG3.2 | 48 | On-ground activities | Wetlands health protected or enhanced | Area (hectares) of wetland enhanced/rehabilitated | Not applicable | Not applicable | OG3.2 | On-ground | Native vegetation enhanced/rehabilitated (include improved fire management practice under this category) | Area (ha) of wetland native vegetation enhanced/rehabilitated | - | See above for definition of ‘wetland’ and ‘native’
OG3.3 | 27 | On-ground activities | Indigenous vegetation enhanced/rehabilitated | Area (hectares) of riparian indigenous vegetation enhanced/rehabilitated | Streambank length (km) of riparian vegetation enhanced/rehabilitated | Streambank length (km) of riparian indigenous vegetation enhanced/rehabilitated | OG3.3 | On-ground | Native vegetation enhanced/rehabilitated (include improved fire management practice under this category) | Area (ha) of riparian native vegetation enhanced/rehabilitated | Streambank length (km) of riparian vegetation enhanced/rehabilitated | See above for definition of ‘riparian’ and ‘native’. Measure both sides of the stream bank, if applicable
OG3.4 | 25 | On-ground activities | Indigenous vegetation enhanced/rehabilitated | Area (hectares) of terrestrial indigenous vegetation enhanced/rehabilitated | Not applicable | Not applicable | OG3.4 | On-ground | Native vegetation enhanced/rehabilitated (include improved fire management practice under this category) | Area (ha) of terrestrial native vegetation enhanced/rehabilitated | - | See above for definition of ‘terrestrial’ and “native’
OG4.1 | 28 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to terrestrial indigenous species | Not applicable | Not applicable | OG4.1 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) of native plantation established | Area (ha) of this vegetation that are locally occurring natives | Plantations are defined as intensively managed stands of trees of either native or exotic species intended for harvest, created by the regular placement of seedlings or seeds, or by regeneration of native vegetation [adapted from National Forest Policy - see NPI website] ‘Locally occurring natives’ is native vegetation that is indigenous to a given area, including trees, shrubs, understorey plants and some specified grasslands
OG4.1 | 29 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to coastal indigenous species | Not applicable | Not applicable | OG4.1 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) of native plantation established | Area (ha) of this vegetation that are locally occurring natives | Plantations are defined as intensively managed stands of trees of either native or exotic species intended for harvest, created by the regular placement of seedlings or seeds, or by regeneration of native vegetation [adapted from National Forest Policy - see NPI website] ‘Locally occurring natives’ is native vegetation that is indigenous to a given area, including trees, shrubs, understorey plants and some specified grasslands
OG4.1 | 30 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to riparian indigenous species | Streambank length (km) of riparian vegetation protected | Streambank length (km) of riparian revegetation | OG4.1 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) of native plantation established | Area (ha) of this vegetation that are locally occurring natives | Plantations are defined as intensively managed stands of trees of either native or exotic species intended for harvest, created by the regular placement of seedlings or seeds, or by regeneration of native vegetation [adapted from National Forest Policy - see NPI website] ‘Locally occurring natives’ is native vegetation that is indigenous to a given area, including trees, shrubs, understorey plants and some specified grasslands
OG4.2 | 29 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to coastal indigenous species | Not applicable | Not applicable | OG4.2 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) planted to coastal native species | Area (ha) of this vegetation that are locally occurring natives | See above definitions of ‘coastal’ and ‘locally occurring natives’
OG4.3 | 30 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to riparian indigenous species | Streambank length (km) of riparian vegetation protected | Streambank length (km) of riparian revegetation | OG4.3 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) planted to wetland native species | Area (ha) of this vegetation that are locally occurring natives | See above definitions of ‘wetland’ and ‘locally occurring natives’
OG4.4 | 30 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to riparian indigenous species | Streambank length (km) of riparian vegetation protected | Streambank length (km) of riparian revegetation | OG4.4 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) planted to riparian native species | Area (ha) of this vegetation that are locally occurring natives | See above definitions of ‘riparian’ and ‘locally occurring natives’
OG4.5 | 30 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to riparian indigenous species | Streambank length (km) of riparian vegetation protected | Streambank length (km) of riparian revegetation | OG4.5 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Stream bank length (km) of riparian vegetation enhanced/rehabilitated | - | Please use this category whenever you have reported activity under OG4.4 (except in States where the protocol of ‘one output code for each output description’ would exclude use). Measure both sides of the stream bank, if applicable
OG4.6 | 28 | On-ground activities | Revegetation with indigenous vegetation | Area (hectares) planted to terrestrial indigenous species | Not applicable | Not applicable | OG4.6 | On-ground | Revegetation with native vegetation (include native pastures under this category, for mixed planting use native or exotic depending on which has highest proportion) | Area (ha) planted to terrestrial native species | Area (ha) of this vegetation that are locally occurring natives | See above for the definitions of ‘terrestrial’ and locally occurring natives’
OG5.1 | 34 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of terrestrial exotic plantation | Not applicable | Not applicable | OG5.1 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic plantation established | - | Plantations are defined as intensively managed stands of trees of either native or exotic species intended for harvest, created by the regular placement of seedlings or seeds, or by regeneration of native vegetation [adapted from National Forest Policy - see NPI website]
OG5.1 | 35 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of coastal exotic plantation | Not applicable | Not applicable | OG5.1 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic plantation established | - | Plantations are defined as intensively managed stands of trees of either native or exotic species intended for harvest, created by the regular placement of seedlings or seeds, or by regeneration of native vegetation [adapted from National Forest Policy - see NPI website]
OG5.1 | 36 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of riparian exotic plantation | Not applicable | Not applicable | OG5.1 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic plantation established | - | Plantations are defined as intensively managed stands of trees of either native or exotic species intended for harvest, created by the regular placement of seedlings or seeds, or by regeneration of native vegetation [adapted from National Forest Policy - see NPI website]
OG5.2 | 33 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of riparian exotic perennial pastures | Not applicable | Not applicable | OG5.2 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic vegetation established | - | -
OG5.2 | 34 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of terrestrial exotic plantation | Not applicable | Not applicable | OG5.2 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic vegetation established | - | -
OG5.2 | 35 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of coastal exotic plantation | Not applicable | Not applicable | OG5.2 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic vegetation established | - | -
OG5.3 | 31 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of terrestrial exotic perennial pastures | Not applicable | Not applicable | OG5.3 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic perennial pastures established | - | Care should be taken to ensure pasture species used to not pose a threat as a potential environmental weed
OG5.3 | 32 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of coastal exotic perennial pastures | Not applicable | Not applicable | OG5.3 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic perennial pastures established | - | Care should be taken to ensure pasture species used to not pose a threat as a potential environmental weed
OG5.3 | 33 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of riparian exotic perennial pastures | Not applicable | Not applicable | OG5.3 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic perennial pastures established | - | Care should be taken to ensure pasture species used to not pose a threat as a potential environmental weed
OG5.4 | 37 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of other terrestrial exotic or mixed indigenous/exotic vegetation planted | Not applicable | Not applicable | OG5.4 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic, non-perennial special purpose pastures established | - | Include exotic annual pasture species, for example those used in rehabilitating saline areas
OG5.4 | 38 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of other coastal exotic or mixed indigenous/exotic vegetation planted | Not applicable | Not applicable | OG5.4 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic, non-perennial special purpose pastures established | - | Include exotic annual pasture species, for example those used in rehabilitating saline areas
OG5.4 | 39 | On-ground activities | Revegetation with exotic vegetation | Area (hectares) of other riparian exotic or mixed indigenous/exotic vegetation planted | Not applicable | Not applicable | OG5.4 | On-ground | Revegetation with exotic vegetation | Area (ha) of exotic, non-perennial special purpose pastures established | - | Include exotic annual pasture species, for example those used in rehabilitating saline areas
OG6.1 | 49 | On-ground activities | Wetlands health protected or enhanced | Area (hectares) of wetlands with reinstated connectivity | Not applicable | Not applicable | OG6.1 | On-ground | Wetlands health protected or enhanced | Area (ha) of wetlands with connectivity reinstated | - | Refers to wetlands where connectivity to the river and / or other wetland systems has been reinstated or substantially enhanced via engineering, management or vegetative means. See also OG2.2 and OG3.2
OG7.1 | 51 | On-ground activities | Management of significant species or ecological communities | Area (hectares) protected by fencing specifically for significant species/community protection | Not applicable | Not applicable | OG7.1 | On-ground | Management of significant species or ecological communities | Area (ha) protected by fencing specifically for significant species/ ecological community protection | - | Includes fencing to exclude feral predators (eg. cats and foxes), native browsers (eg. Possums), 4WD’s, etc, and to enhance management capability
OG7.2 | 53 | On-ground activities | Management of significant species or ecological communities | Number of successful individuals bred through an established breeding program | Not applicable | Not applicable | OG7.2 | On-ground | Management of significant species or ecological communities | Number of breeding programs developed | Number of individuals bred | Ensure that the species being bred is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG7.3 | 52 | On-ground activities | Management of significant species or ecological communities | Number of individuals translocated or established | Not applicable | Not applicable | OG7.3 | On-ground | Management of significant species or ecological communities | Number of translocation programs developed | Number of individuals translocated or established | Ensure that the species being translocated has noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG7.4 | 54 | On-ground activities | Management of significant species or ecological communities | Number of seedbanks managed | Weight (kg) of seeds collected | Weight (kg) of seeds collected | OG7.4 | On-ground | Management of significant species or ecological communities | Number of seedbanks developed | - | -
OG8.1 | 55 | On-ground activities | Significant pest plant control | Area (hectares) of pest plant control | Type of pest plant (e.g. blackberry, boxthorn etc) | Type of pest plant (e.g. blackberry, boxthorn etc) | OG8.1 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest plant control measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates) and whether the control measure is ‘eradication’ versus ‘containment’
OG8.1 | 55.01 | On-ground activities | Significant pest plant control | Area (hectares) of boxthorns control | Not applicable | Not applicable | OG8.1 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest plant control measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates) and whether the control measure is ‘eradication’ versus ‘containment’
OG8.1 | 55.02 | On-ground activities | Significant pest plant control | Area (hectares) of wheel cactus control | Not applicable | Not applicable | OG8.1 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest plant control measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates) and whether the control measure is ‘eradication’ versus ‘containment’
OG8.1 | 55.03 | On-ground activities | Significant pest plant control | Area (hectares) of blackberry control | Not applicable | Not applicable | OG8.1 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest plant control measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates) and whether the control measure is ‘eradication’ versus ‘containment’
OG8.1 | 55.04 | On-ground activities | Significant pest plant control | Area (hectares) of bridal creeper control | Not applicable | Not applicable | OG8.1 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest plant control measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates) and whether the control measure is ‘eradication’ versus ‘containment’
OG8.1 | 55.05 | On-ground activities | Significant pest plant control | Area (hectares) of broad-leaved weed control | Not applicable | Not applicable | OG8.1 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest plant control measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates) and whether the control measure is ‘eradication’ versus ‘containment’
OG8.1 | 55.06 | On-ground activities | Significant pest plant control | Area (hectares) of woody weed control | Not applicable | Not applicable | OG8.1 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest plant control measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates) and whether the control measure is ‘eradication’ versus ‘containment’
OG8.1 | 55.07 | On-ground activities | Significant pest plant control | Area (hectares) of Salvinia molesta control | Not applicable | Not applicable | OG8.1 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest plant control measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates) and whether the control measure is ‘eradication’ versus ‘containment’
OG8.2 | 55 | On-ground activities | Significant pest plant control | Area (hectares) of pest plant control | Type of pest plant (e.g. blackberry, boxthorn etc) | Type of pest plant (e.g. blackberry, boxthorn etc) | OG8.2 | On-ground | Significant pest plant, animal and disease control | Number of weed seed wash down facilities established or renovated | - | -
OG8.2 | 55.01 | On-ground activities | Significant pest plant control | Area (hectares) of boxthorns control | Not applicable | Not applicable | OG8.2 | On-ground | Significant pest plant, animal and disease control | Number of weed seed wash down facilities established or renovated | - | -
OG8.2 | 55.02 | On-ground activities | Significant pest plant control | Area (hectares) of wheel cactus control | Not applicable | Not applicable | OG8.2 | On-ground | Significant pest plant, animal and disease control | Number of weed seed wash down facilities established or renovated | - | -
OG8.2 | 55.03 | On-ground activities | Significant pest plant control | Area (hectares) of blackberry control | Not applicable | Not applicable | OG8.2 | On-ground | Significant pest plant, animal and disease control | Number of weed seed wash down facilities established or renovated | - | -
OG8.2 | 55.04 | On-ground activities | Significant pest plant control | Area (hectares) of bridal creeper control | Not applicable | Not applicable | OG8.2 | On-ground | Significant pest plant, animal and disease control | Number of weed seed wash down facilities established or renovated | - | -
OG8.2 | 55.05 | On-ground activities | Significant pest plant control | Area (hectares) of broad-leaved weed control | Not applicable | Not applicable | OG8.2 | On-ground | Significant pest plant, animal and disease control | Number of weed seed wash down facilities established or renovated | - | -
OG8.2 | 55.06 | On-ground activities | Significant pest plant control | Area (hectares) of woody weed control | Not applicable | Not applicable | OG8.2 | On-ground | Significant pest plant, animal and disease control | Number of weed seed wash down facilities established or renovated | - | -
OG8.2 | 55.07 | On-ground activities | Significant pest plant control | Area (hectares) of Salvinia molesta control | Not applicable | Not applicable | OG8.2 | On-ground | Significant pest plant, animal and disease control | Number of weed seed wash down facilities established or renovated | - | -
OG8.3 | 56 | On-ground activities | Significant pest vertebrate control | Area (hectares) of pest animal control | Type of pest animal (e.g.rabbits, foxes) | Type of pest animal (e.g.rabbits, foxes) | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.01 | On-ground activities | Significant pest plant control | Area (hectares) of cane toad control | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.02 | On-ground activities | Significant pest plant control | Area (hectares) of cat control | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.03 | On-ground activities | Significant pest plant control | Area (hectares) of deer control | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.04 | On-ground activities | Significant pest plant control | Area (hectares) of fox control | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.05 | On-ground activities | Significant pest plant control | Area (hectares) of goat control | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.06 | On-ground activities | Significant pest plant control | Area (hectares) of hare control | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.07 | On-ground activities | Significant pest vertebrate control | Area (hectares) of rabbit control | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.08 | On-ground activities | Significant pest vertebrate control | Area (hectares) of yellow-throated minor control | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.09 | On-ground activities | Significant pest vertebrate control | Area (hectares) of pigs control | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.3 | 56.1 | On-ground activities | Significant pest vertebrate control | Area (hectares) of hooved animal control (Camel, Donkeym Horse and Buffalo) | Not applicable | Not applicable | OG8.3 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest animal control (vertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.4 | 56 | On-ground activities | Significant pest vertebrate control | Area (hectares) of pest animal control | Type of pest animal (e.g.rabbits, foxes) | Type of pest animal (e.g.rabbits, foxes) | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.01 | On-ground activities | Significant pest plant control | Area (hectares) of cane toad control | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.02 | On-ground activities | Significant pest plant control | Area (hectares) of cat control | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.03 | On-ground activities | Significant pest plant control | Area (hectares) of deer control | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.04 | On-ground activities | Significant pest plant control | Area (hectares) of fox control | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.05 | On-ground activities | Significant pest plant control | Area (hectares) of goat control | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.06 | On-ground activities | Significant pest plant control | Area (hectares) of hare control | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.07 | On-ground activities | Significant pest vertebrate control | Area (hectares) of rabbit control | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.08 | On-ground activities | Significant pest vertebrate control | Area (hectares) of yellow-throated minor control | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.09 | On-ground activities | Significant pest vertebrate control | Area (hectares) of pigs control | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.4 | 56.1 | On-ground activities | Significant pest vertebrate control | Area (hectares) of hooved animal control (Camel, Donkeym Horse and Buffalo) | Not applicable | Not applicable | OG8.4 | On-ground | Significant pest plant, animal and disease control | Area (ha) of pest control (invertebrates) measures implemented | - | Ensure that the species being controlled is noted in the output description field (in Part C of the Project Schedule and reporting templates)
OG8.5 | 55 | On-ground activities | Significant pest plant control | Area (hectares) of pest plant control | Type of pest plant (e.g. blackberry, boxthorn etc) | Type of pest plant (e.g. blackberry, boxthorn etc) | OG8.5 | On-ground | Significant pest plant, animal and disease control | Area (ha) of plant disease control measures implemented | - | Includes actions taken to prevent the spread of plant diseases such as phytophthora. Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.5 | 55.01 | On-ground activities | Significant pest plant control | Area (hectares) of boxthorns control | Not applicable | Not applicable | OG8.5 | On-ground | Significant pest plant, animal and disease control | Area (ha) of plant disease control measures implemented | - | Includes actions taken to prevent the spread of plant diseases such as phytophthora. Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.5 | 55.02 | On-ground activities | Significant pest plant control | Area (hectares) of wheel cactus control | Not applicable | Not applicable | OG8.5 | On-ground | Significant pest plant, animal and disease control | Area (ha) of plant disease control measures implemented | - | Includes actions taken to prevent the spread of plant diseases such as phytophthora. Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.5 | 55.03 | On-ground activities | Significant pest plant control | Area (hectares) of blackberry control | Not applicable | Not applicable | OG8.5 | On-ground | Significant pest plant, animal and disease control | Area (ha) of plant disease control measures implemented | - | Includes actions taken to prevent the spread of plant diseases such as phytophthora. Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.5 | 55.04 | On-ground activities | Significant pest plant control | Area (hectares) of bridal creeper control | Not applicable | Not applicable | OG8.5 | On-ground | Significant pest plant, animal and disease control | Area (ha) of plant disease control measures implemented | - | Includes actions taken to prevent the spread of plant diseases such as phytophthora. Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.5 | 55.05 | On-ground activities | Significant pest plant control | Area (hectares) of broad-leaved weed control | Not applicable | Not applicable | OG8.5 | On-ground | Significant pest plant, animal and disease control | Area (ha) of plant disease control measures implemented | - | Includes actions taken to prevent the spread of plant diseases such as phytophthora. Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.5 | 55.06 | On-ground activities | Significant pest plant control | Area (hectares) of woody weed control | Not applicable | Not applicable | OG8.5 | On-ground | Significant pest plant, animal and disease control | Area (ha) of plant disease control measures implemented | - | Includes actions taken to prevent the spread of plant diseases such as phytophthora. Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG8.5 | 55.07 | On-ground activities | Significant pest plant control | Area (hectares) of Salvinia molesta control | Not applicable | Not applicable | OG8.5 | On-ground | Significant pest plant, animal and disease control | Area (ha) of plant disease control measures implemented | - | Includes actions taken to prevent the spread of plant diseases such as phytophthora. Ensure that the species being controlled is noted in the output description field (in both Part C of the Project Schedule and reporting templates)
OG9.1 | 57 | On-ground activities | Soil management | Area (hectares) of land treated for soil erosion through engineering works | Number of sites | Number of soil erosion engineering sites | OG9.1 | On-ground | Works related to soil management and other soil treatments | Area (ha) of land treated and/ or protected from soil erosion by engineering works | - | With work such as rehabilitation of gullies by filling in and reshaping of the sides, count the actual number of ha treated. With other works, such as the construction of contour banks, count the number of ha protected from erosion
OG9.2 | 58 | On-ground activities | Soil management | Area (hectares) of land treated for soil erosion through exclusion fencing | Number of sites | Number of soil erosion exclusion fencing sites | OG9.2 | On-ground | Works related to soil management and other soil treatments | Area (ha) of land treated for soil erosion through exclusion fencing | - | Includes areas fenced to control stock and/ or enable revegetation treatment
OG9.3 | 59 | On-ground activities | Soil management | Area (hectares) of treatment for acid sulfate soils | Not applicable | Not applicable | OG9.3 | On-ground | Works related to soil management and other soil treatments | Area (ha) of acid sulphate soils identified and treated/protected | - | Includes areas mapped and/ or treated with soil ameliorants and/ or treated with works
OG9.4 | 60 | On-ground activities | Soil management | Area (hectares) of soil treatment for other than erosion, salinity or acid sulfate soils | Not applicable | Not applicable | OG9.4 | On-ground | Works related to soil management and other soil treatments | Area (ha) of soil treatment for other than erosion or acid sulphate soils | - | Includes activities such as spreading lime, gypsum or clay
Other | 0 | Other | Other | Other | Other | Other | Other | Other |  | [Your output measure] | [Your output measure] | This category is to be used only in the unlikely event that your activity does not fit into any of the above categories. You must provide a detailed written description of the output to explain why it cannot fit into an existing output category and sent it to the MandE coordinator in your State or Territory who will review the new outputs.
P1.1 | 82 | Planning | Improved practice codes or guidelines | Number of best management practice codes developed | Not applicable | Not applicable | P1.1 | Planning | Improved codes of practice or guidelines | Number of best management practice codes or guidelines completed | - | All guidelines/ codes/ protocols eg. sustainable farming, rabbit control, private forestry, greenhouse, environmental etc. If the review is a considerable review of existing codes or guidelines, at your discretion that can be counted
P1.1 | 83 | Planning | Improved practice codes or guidelines | Number of best management practice guidelines developed | Not applicable | Not applicable | P1.1 | Planning | Improved codes of practice or guidelines | Number of best management practice codes or guidelines completed | - | All guidelines/ codes/ protocols eg. sustainable farming, rabbit control, private forestry, greenhouse, environmental etc. If the review is a considerable review of existing codes or guidelines, at your discretion that can be counted
P2.1 | 84 | Planning | Integrated catchment or sub-catchment plans | Number of catchment plans developed | Not applicable | Not applicable | P2.1 | Planning | Regional plans | Number of regional strategies or investment plans accredited | - | Strategies/ plans developed by regional NRM groups/ catchment management authorities to achieve accreditation status and the first regional investment funding
P2.2 | 84 | Planning | Integrated catchment or sub-catchment plans | Number of catchment plans developed | Not applicable | Not applicable | P2.2 | Planning | Regional plans | Number of regional strategies or investment plans reviewed or revised | - | Significant review or revision of regional level strategies/ plans such as the rolling annual review of investment plans/strategies
P3.1 | 84 | Planning | Integrated catchment or sub-catchment plans | Number of catchment plans developed | Not applicable | Not applicable | P3.1 | Planning | Sub-regional plans | Number of catchment or sub-catchment plans or strategies completed | - | Plans/ strategies at catchment(s) or sub-catchment(s) scale, which do not reach full regional level eg. action or management plans, a river management strategy, roadside management, weed management, catchment salinity control. Includes reviews of existing plans that generate enhancement of plans or strategies
P3.1 | 85 | Planning | Integrated catchment or sub-catchment plans | Number of sub-catchment plans developed | Not applicable | Not applicable | P3.1 | Planning | Sub-regional plans | Number of catchment or sub-catchment plans or strategies completed | - | Plans/ strategies at catchment(s) or sub-catchment(s) scale, which do not reach full regional level eg. action or management plans, a river management strategy, roadside management, weed management, catchment salinity control. Includes reviews of existing plans that generate enhancement of plans or strategies
P3.2 | 86 | Planning | Property management plans | Number of property management plans completed | Not applicable | Not applicable | P3.2 | Planning | Sub-regional plans | Number of property or reserve management plans completed | - | Plans at whole farm/ property or reserve scale eg. farm/ reserve plans or management plans for particular issues eg. weeds, grazing, vegetation, drainage. Includes reviews of existing plans that generate enhancement of plans or strategies
P4.1 | 87 | Planning | Species recovery plans and action statements | Number of endangered species recovery plans developed | Not applicable | Not applicable | P4.1 | Planning | Resource management plans | Number of recovery or management plans for threatened species or ecological communities completed | Number of species or communities covered by the plan | Management of specific species or ecological communities eg. interim recovery plans or recovery plans for threatened species, endangered species action statements. Includes reviews of existing plans that generate enhancement of plans or strategies
P4.1 | 88 | Planning | Species recovery plans and action statements | Number of endangered species action statements developed | Not applicable | Not applicable | P4.1 | Planning | Resource management plans | Number of recovery or management plans for threatened species or ecological communities completed | Number of species or communities covered by the plan | Management of specific species or ecological communities eg. interim recovery plans or recovery plans for threatened species, endangered species action statements. Includes reviews of existing plans that generate enhancement of plans or strategies
P4.2 | 86 | Planning | Property management plans | Number of property management plans completed | Not applicable | Not applicable | P4.2 | Planning | Resource management plans | Number of other resource management plans completed | - | Management of a particular NRM asset, issue or threat, including at a statewide level eg. estuarine management, State Weeds Strategy, wind erosion strategy, a wetland management plan, or regional fire management plan. Includes reviews of existing plans that generate enhancement of plans or strategies
P5.1 | 86 | Planning | Property management plans | Number of property management plans completed | Not applicable | Not applicable | P5.1 | Planning | Other plans | Number of other biophysical, economic or socially related plans completed | - | Can include monitoring and evaluation plans, research and development plans, sustainable development plans or a community capacity building plan. Includes reviews of existing plans that generate enhancement of plans or strategies (not for the management of an organisation – see CB3.1)
RA1.1 | 89 | Resource assessment | Baseline, trend or condition studies for targets | Number of studies | Not applicable | Not applicable | RA1.1 | Resource assessment | Setting or monitoring resource condition targets | Number of studies completed | Number of sites monitored | Studies undertaken specifically to enable the setting of resource condition targets in a regional plan. All other studies belong under RA2
RA1.1 | 90 | Resource assessment | Baseline, trend or condition studies for targets | Number of sites monitored | Not applicable | Not applicable | RA1.1 | Resource assessment | Setting or monitoring resource condition targets | Number of studies completed | Number of sites monitored | Studies undertaken specifically to enable the setting of resource condition targets in a regional plan. All other studies belong under RA2
RA1.2 | 102 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of other studies | Area (hectares) surveyed | Area (hectares) surveyed by other studies | RA1.2 | Resource assessment | Setting or monitoring resource condition targets | Number of new monitoring programs established | - | Use where there was no existing monitoring program
RA1.3 | 102 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of other studies | Area (hectares) surveyed | Area (hectares) surveyed by other studies | RA1.3 | Resource assessment | Setting or monitoring resource condition targets | Number of existing monitoring programs enhanced | - | Use where an existing monitoring program has been significantly expanded or enhanced
RA2.1 | 94 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of vegetation studies | Area (hectares) surveyed | Area (hectares) surveyed by vegetation studies | RA2.1 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of biophysical studies completed | Area (ha) surveyed | Eg. studies of vegetation, salinity, soil, groundwater, marine areas
RA2.1 | 95 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of salinity studies | Area (hectares) surveyed | Area (hectares) surveyed by salinity studies | RA2.1 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of biophysical studies completed | Area (ha) surveyed | Eg. studies of vegetation, salinity, soil, groundwater, marine areas
RA2.1 | 96 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of species studies | Area (hectares) surveyed | Area (hectares) surveyed by species studies | RA2.1 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of biophysical studies completed | Area (ha) surveyed | Eg. studies of vegetation, salinity, soil, groundwater, marine areas
RA2.1 | 97 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of soil studies | Area (hectares) surveyed | Area (hectares) surveyed by soil studies | RA2.1 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of biophysical studies completed | Area (ha) surveyed | Eg. studies of vegetation, salinity, soil, groundwater, marine areas
RA2.1 | 98 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of marine studies | Area (hectares) surveyed | Area (hectares) surveyed by marine studies | RA2.1 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of biophysical studies completed | Area (ha) surveyed | Eg. studies of vegetation, salinity, soil, groundwater, marine areas
RA2.1 | 99 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of groundwater studies | Area (hectares) surveyed | Area (hectares) surveyed by groundwater studies | RA2.1 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of biophysical studies completed | Area (ha) surveyed | Eg. studies of vegetation, salinity, soil, groundwater, marine areas
RA2.1 | 100 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of surface water / inland aquatic studies | Area (hectares) surveyed | Area (hectares) surveyed by surface water / inland aquatic studies | RA2.1 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of biophysical studies completed | Area (ha) surveyed | Eg. studies of vegetation, salinity, soil, groundwater, marine areas
RA2.1 | 102 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of other studies | Area (hectares) surveyed | Area (hectares) surveyed by other studies | RA2.1 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of biophysical studies completed | Area (ha) surveyed | Eg. studies of vegetation, salinity, soil, groundwater, marine areas
RA2.2 | 101 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of social studies | Area (hectares) surveyed | Area (hectares) surveyed by social studies | RA2.2 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of social /economic studies completed | Size of population covered by the survey sample | -
RA2.3 | 102 | Resource assessment | Investigations (survey, inventory and mapping and data analysis) | Number of other studies | Area (hectares) surveyed | Area (hectares) surveyed by other studies | RA2.3 | Resource assessment | Investigations (survey, inventory and mapping, and data analysis) | Number of reports completed | - | These could include a synthesis of previous studies or meta-analysis of previous studies
RA3.1 | 91 | Resource assessment | Decision support tools | Number of models developed | Not applicable | Not applicable | RA3.1 | Resource assessment | Decision support tools | Number of models developed | - | -
RA3.2 | 92 | Resource assessment | Decision support tools | Number of information management systems developed | Not applicable | Not applicable | RA3.2 | Resource assessment | Decision support tools | Number of information management systems developed | - | Systems to hold natural resource information. See CB4.4 for other databases. Includes addition of new modules to existing systems
RA3.3 | 93 | Resource assessment | Decision support tools | Number of other decision support tools developed | Not applicable | Not applicable | RA3.3 | Resource assessment | Decision support tools | Number of other decision support tools developed | - | For governance related decision-making tools, use CB4.1
RA4.1 | 103 | Resource assessment | Research and development studies | Number of research and development studies undertaken | Not applicable | Not applicable | RA4.1 | Resource assessment | Research and development studies | Number of research and development studies completed | - | Includes completion of the research report